## Overview
Function Point Overview
Use Case: | FP | Hours spent: |  |  |  | Adjust Function manually
|  | Documentation | Coding | Testing | Total | Expectation
Login | 66.88 | 1 | 2 | 0.5 | 3.5
Register | 69.52 | 1.5 | 3 | 1 | 5.5
Check Leaderboard | 64.24 | 1 | 2.5 | 0.5 | 4
Edit personal Data | 69.52 | 1 | 4.5 | 1.5 | 7
Manage User Data | 84.48 | 1 | 6.5 | 2 | 9.5
Give Feedback | 71.1 | 1.5 | 3 | 0.5 | 5
Give Support | 99 | 1.5 | 6 | 2 | 9.5
Check Game Results | 51.92 | 1 | 1 | 0.5 | 2.5 | 2.2831
Bet on Win | 76.05 | 1.5 | 5 | 1 | 7.5 | 6.4721
Wager Bet | 87.1 | 1 | 2 | 0.5 | 3.5 | 8.3904
Buy/Get Reward | 63.7 | 1 | 3.5 | 0.5 | 5 | 4.3281
| Ausreißer | Begrüdung
| Wager Bet | Code von Place Bet wieder verwendbar, daher Coding Aufwand deutlich geringer.

## Login
UC: Login
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 10
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 3 | 0 | 0 | low | 0
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 2 | 0 | 1 | low | 2
[5 empty] | Function Points: | 66.88

## Register
UC: Register
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 10
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 5 | 0 | 0 | low | 1
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 2 | 0 | 0 | low | 2
[5 empty] | Function Points: | 69.52

## Check Leaderboard
UC: Check Leaderboard
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 10
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 1 | 0 | 0 | low | 0
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 0 | 0 | 1 | low | 1
64.24

## Edit personal Data
UC: Edit personal Data
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 10
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 5 | 1 | 0 | low | 2
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 4 | 1 | 0 | low | 1
69.52

## Manage User Data
UC: Manage User Data
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 2 | low | 12
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 6 | 1 | 0 | low | 2
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 4 | 1 | 1 | low | 2
84.48

## Give Feedback
UC: Give Feedback
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 1 | 2 | 0 | low | 10
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 2 | 0 | 0 | low | 1
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 2 | 0 | 0 | low | 2
71.1

## Answer Ticket
UC: Answer Ticket
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 2 | low | 14
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 4 | 0 | 0 | low | 2
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 2 | 1 | 1 | low | 2
99

## Check Game Results
UC: Check Game Results
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 8
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 0 | 0 | 0 | low | 0
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 0 | 0 | 1 | low | 1
51.92

## Bet on Win
UC: Bet on Win
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 15
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 4 | 1 | 0 | low | 1
External Outputs | EO | 0 | 0 | 0 | low | 0
External Queries | EQ | 2 | 0 | 2 | low | 3
76.05

## Wager Bet
UC: Wager Bet on Win
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 16
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 5 | 1 | 0 | low | 2
External Outputs | EO | 1 | 0 | 0 | low | 1
External Queries | EQ | 3 | 0 | 2 | low | 4
87.1

## Buy - Get Reward
UC: Buy / Get Reward
|  | DET | RET | FTR | Complexity | Count
Data Functionality
Internal Logical Files | ILF | 0 | 0 | 1 | low | 12
External Interface Files | EIF | 0 | 0 | 0 | low | 0
Transaction Functionality
External Inputs | EI | 2 | 0 | 0 | low | 1
External Outputs | EO | 1 | 1 | 0 | low | 2
External Queries | EQ | 1 | 0 | 0 | low | 1
63.7