## Tabelle1
Risk Name | Risk Description | Rist Probability of Occurrence | Risk Impact (1-10) | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Overwriting of code | loss of code | 0.6 | 2 | 1.2 | Version Controlling | André Helbig
Hardware failure | PC or Server breaks | 0.1 | 5 | 0.5 | Version Controlling and spare PC | André Helbig
Illness | Short term loss of workforce due to illness | 0.7 | 2 | 1.4 | Stay healthy | Felix Morsbach
Accidents | Long term loss of workforce due to an accident | 0.03 | 9 | 0.27 | Find replacement | Felix Morsbach
Deadline not met | Project is not finished at deadline | 0.2 | 7 | 1.4 | Continuous progress tracking | Felix Morsbach
Errors | On reaching the deadline errors are still found | 0.3 | 4 | 1.2 | Early testing | André Helbig
Problem with external Data Source | Game data can not be fetched the regular way | 0.21 | 3 | 0.63 | Plan B for getting necessary data | Felix Morsbach
Exmatriculation | Exmatriculation due to bad grades | 0.07 | 9 | 0.63 | Study | André Helbig